## Weekly Construction Report
[5 empty] | Type of Work | [5 empty] | Project |  |  | Region |  | Dist.
[5 empty] | Contractor | [5 empty] | Contract # |  |  |  | WAC / Job No.
[5 empty] | Consultant Representative | [5 empty] | From
[5 empty] | Report# |  |  | Week Ending |  |  | To
[5 empty] | Other Projects in same Contract - File | [5 empty] | C.S. |  | km |  | To C.S. |  | km
WEEKLY CONSTRUCTION REPORT | [12 empty] | Total Length |  |  |  | km
Date | [8 empty] | GRADING, GRAVEL SURFACING, BASE COURSE, SURFACING & SEAL COAT
EQUIPMENT | SUN OP. HRS | MON OP. HRS | TUES OP. HRS | WED OP. HRS | THURS OP. HRS | FRI OP. HRS | SAT OP. HRS | TOTALS | TASK | Km | UNIT | TOTAL PROJECT |  | TOTAL QUANTITIES PLACED |  |  | % COMPLETED
[12 empty] | Initial Estimate | Current Estimate | This Week | This Fiscal Year | Total Project to Date | One Week Ago | To Date
REMARKS ON CONRACTOR'S PROGRESS, SITE OCCUPANCY, LANE CLOSURE AND WEATHER TO BE | [8 empty] | STARTING DATE: |  | Estimated: |  |  | Actual: |  |  | Shut Down for Season
RECORDED ON FORM A.07 (SITE OCCUPANCY AND LANE RENTAL WEEKLY REPORT BRIDGES AND CONSTRUCTION) | [8 empty] | COMPLETION DATE: |  | Estimated: |  |  | Actual: |  |  | Date:
CONTRACTOR COMMENTS
Consultant: | [5 empty] | Date: |  |  | Contractor Representative: | [5 empty] | Date:
Revised December 2013 | [15 empty] | AppendixA.06

## Weekly Construction SAMPLE
[5 empty] | Type of Work |  | Grading, Bridges and Other Work |  |  |  | Project | Hwy XX:XX |  | Region | NAME | Dist. | NAME
[5 empty] | Contractor |  | NAME |  |  |  | Contract # | CON00XXXXX |  |  | WAC / Job No. |  | WAC00XXXXX
[5 empty] | Consultant Representative |  |  | NAME |  |  | From | Hwy XX:XX
[5 empty] | Report# | # |  | Week Ending | DATE |  | To | Hwy XX:XX
[5 empty] | Other Projects in same Contract - File | [5 empty] | C.S. |  | km |  | To C.S. |  | km
WEEKLY CONSTRUCTION REPORT | [12 empty] | Total Length |  |  |  | km
Date | [8 empty] | GRADING, GRAVEL SURFACING, BASE COURSE, SURFACING & SEAL COAT
EQUIPMENT | SUN OP. HRS | MON OP. HRS | TUES OP. HRS | WED OP. HRS | THURS OP. HRS | FRI OP. HRS | SAT OP. HRS | TOTALS | TASK | Km | UNIT | TOTAL PROJECT |  | TOTAL QUANTITIES PLACED |  |  | %COMPLETED
621 Scraper |  |  | 6 | 8 | 12 | 8 | 5 | 39 |  |  |  | Initial Estimate | Current Estimate | This Week | This Fiscal Year | Total Project to Date | One Week Ago | To Date
621 Scraper |  |  |  | 8 |  |  |  | 8
621 Scraper | [7 empty] | 0
621 Scraper | [7 empty] | 0 | Roadway
627 Scraper |  | 12 | 12 | 12 | 12 | 8 | 5 | 61 | Common Excavation |  | m3 | 233100 | 233100 | 5000 | 18000 | 35000 | 12.9% | 15.02%
400 Rock Truck |  | 12 | 12 | 12 | 12 | 12 | 5 | 65 | Borrow Excavation |  | m3 | 90300 | 90300 | 5000 | 7000 | 16000 | 12.2% | 17.72%
400 Rock Truck |  | 6 | 6 | 12 | 12 | 5 | 5 | 46
400 Rock Truck |  |  |  |  | 6 | 5 | 5 | 16 | Culverts
D7 Dozer |  |  |  |  | 8 |  |  | 8 | 600mm |  | m | 796 | 796 | 24 | 344 | 344 | 40.2% | 43.22%
D6 Dozer |  | 12 | 12 | 12 | 12 | 7 | 5 | 60 | 800 |  | m | 443 | 500 | 24 | 144 | 242 | 43.6% | 48.4%
D5 Dozer |  |  |  | 6 | 12 | 12 | 5 | 35 | 1200 |  | m | 49 | 98 | 0 | 98 | 98 | 100% | 100%
330 Hoe |  | 12 | 12 | 12 | 12 | 12 | 2 | 62
270 Hoe |  | 12 | 12 | 12 | 12 | 12 | 3 | 63 | BFXXXXX |  | LS | 1 | 1 | 0 | 1 | 1 | 100% | 100%
140H Grader |  | 12 | 10 | 8 | 8 | 4 |  | 42
14G Grader |  | 12 | 12 | 12 | 12 | 12 | 5 | 65
815 Packer |  | 12 | 12 | 12 | 12 | 12 | 5 | 65 | BFXXXXX |  | LS | 1 | 1 | 0 | 1 | 1 | 100% | 100%
Protec Packer |  | 12 | 6 | 6 |  | 12 |  | 36
JD and sheepsfoot packer |  | 12 | 12 | 12 | 12 | 12 | 5 | 65
Water Truck | [7 empty] | 0
REMARKS ON CONRACTOR'S PROGRESS, SITE OCCUPANCY, LANE CLOSURE AND WEATHER TO BE | [8 empty] | STARTING DATE: |  | Estimated: | DATE |  | Actual: | DATE |  | Shut Down for Season
RECORDED ON FORM A.07 (SITE OCCUPANCY AND LANE RENTAL WEEKLY REPORT BRIDGES AND CONSTRUCTION) | [8 empty] | COMPLETION DATE: |  | Estimated: | DATE |  | Actual: | DATE |  | Date: | DATE
CONTRACTOR COMMENTS:
Consultant: | [5 empty] | Date: |  |  | Contractor Representative: | [5 empty] | Date:
Revised December 2013 | [15 empty] | AppendixA.06
SAMPLE