## Instructions
Instructions:
Commencement of New Project
Enter project information in:
Site Occupancy Days (Total Days Bid): - into Cell R7
Site Occupancy Days (Unit Price): - into Cell R9
Lane Closure (Total Lanes Bid): - into Cell R17
Lane Closure (Unit Price): - into Cell R19
Project: - into Cell C27
Highway Number: Control Section or Bridge File: - into Cell M27
Contractor: - into Cell C28
Contract Number: - into Cell M28
Consultant/Inspector - into Cell L29
Change to Contract
Enter additional project information in:
Additional Site Occupancy Days Approved (Total Additional Days): - into Cell R8
Additional Lane Closures Approved (Total Additional Lanes): - into Cell R18
Revise Inspector name appropriately: - into Cell L29
Start of Each New Week
Copy and paste new Week spreadsheet into Workbook by:
right click last week spreadsheet tab
pick 'Move or Copy'
pick '(move to end)'
pick 'Create a Copy'
pick 'OK'
Rename spreadsheet tab to Week ##
right click new spreadsheet tab
pick 'Rename'
type in week number
Enter the last Weekly Report number - into Cell H3
Enter the four Site Occupancy values from the last Week Report spreadsheet - into Cell H7 to H13
Enter the Lane Closure tracking information - into Cell H17 and H19
Enter Week Ending date - into Cell C29
Enter status of day by:
Yes/No for a Site Occupancy Day - into Cells G33, G39, G45, G51, G57, G63 and G69
Yes/No for Scheduled Day Off - into Cells G34, G40, G46, G52, G58, G64 and G70
Yes/No for Inclement Weather Day - into Cells G35, G41, G47, G53, G59, G65 and G71
Enter weather conditions appropriately for each day
Enter daily progress and comments appropriately including number of Lane Closures for each day.
* NEW | Enter weekly Labour Data as appropriate - into cells AE6, AE11, AF6, AF11
Review
Print off and provide to contractor for comments and signing
Comments:
Only the cells needing information are unlocked - highlighted in yellow - all others are locked.
The spreadsheet tracks the SO Days, the 8 day off cycle and the 30 day cycle each day, as well as the penalty
associated with SO. It automatically tracks the 8 and 30 day cycles and gives warnings when errors are made
in the inputs of SO/Days Off/Inclement Weather. It also tracks and gives warnings with respect to days off,
including, Phase Breaks and Winter Shutdown based upon the inputs to SO/Days Off/Inclement Weather.
Lane Closures are tracked in the Weekly Data input area (H17 and H19). The number of Closures each day can
be noted in the Daily Progress and Comments section of the report.
If additional comment space is needed, row height can be adjusted to provide more space.
A Sample spreadsheet is provided for reference but can be deleted when not needed.

## Week 1
Weekly Data: | [11 empty] | Project Data: | [5 empty] | Labour Data:
Weekly Progress Report Number | [6 empty] | Enter: Last Week's Weekly Progress Number
(Last Week): | [17 empty] | Labour Data Summary - Consultant
[19 empty] | Brought Forward | This Week | Total to Date
Site Occupancy Days Tracking | [11 empty] | Site Occupancy Days | [5 empty] | Total Number of Staff Days |  |  | 0 | Enter: Total Number of staff days on this Contract this week
Site Occupancy Days | [6 empty] | Enter: Number of Site Occupancy Days Used to Date |  |  |  |  | Total Days Bid: | Enter: Project Total Number of Site Occupancy Days Bid |  |  |  |  | Example: 5 staff per day times 6 days this week = 30 staff days per week |  |  |  | This includes office, aggregate and on-site field staff
(Brought Forward): | [11 empty] | Additional Days Approved: | Enter: Additional Number of Site Occupancy Days Approved
Site Occupancy 30 Day Cycle | [6 empty] | Enter: Day Number in 30 Day Cycle Brought Forward (as of last report) |  |  |  |  | Unit Price: | Enter: Unit Price from Unit Price Schedule |  |  |  |  | Labour Data Summary - Contractor
(Brought Forward): | [18 empty] | Brought Forward | This Week | Total to Date
Pre Scheduled Days Off Cycle | [6 empty] | Enter: Number of Pre Scheduled Days Off Used to Date in 8 Day Cycle | [10 empty] | Total Number of Staff Days |  |  | 0 | Enter: Total Number of staff days on this Contract this week
(Brought Forward): | [17 empty] | Example: 10 staff per day times 6 days this week = 60 staff days per week |  |  |  | This includes office, aggregate, on-site field staff
Inclement Weather Days | [6 empty] | Enter: Number of Inclement Days Brought Forward (as of last report)
(Brought Forward):
Lane Closure Tracking | [11 empty] | Lane Closure
Lane Closures | [6 empty] | Enter: Number of Lane Closures Brought Forward (as of last report) |  |  |  |  | Total Lanes Bid: | Enter: Project Total Number of Lane Closures Bid
(Brought Forward): | [11 empty] | Additional Lanes Approved: | Enter: Additional Number of Lane Closures Approved
Lane Closures | [6 empty] | Enter: Number of Lane Closures This Week |  |  |  |  | Unit Price: | Enter: Unit Price from Unit Price Schedule
(This Week):
[5 empty] | Site Occupancy and Lane Closure Weekly | [5 empty] | Report # 1
Project: | [7 empty] | Hwy #:CS or Bridge File: | [7 empty] | 0 | Site Occupancy Days (Brought Forward)
Contractor: | [7 empty] | Contract Number: | [7 empty] | 0 | Pre Scheduled 8 Days Off Cycle (Brought Forward)
Week Ending: | 2016-07-16 | [6 empty] | Consultant: | [7 empty] | 0 | Inclement Weather Days (Brought Forward)
DATE & DAY | [5 empty] | DAILY PROGRESS AND COMMENTS | [9 empty] | 0 | Site Occupancy 30 Day Cycle (Last Week)
2016-07-10 | [14 empty] | This Week | Total to Date
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0 |  | If Zero, Project is on Preschedule Phase Break or Winter Shutdown
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0 | Tracking of 30 Day Cycle
2016-07-11
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
2016-07-12
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
2016-07-13
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
2016-07-14
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
2016-07-15
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
2016-07-16
Weather | SO Day |  |  |  | No | [8 empty] | Site Occupancy | 0 | 0
| Day Off |  |  |  | No | [8 empty] | Pre Scheduled Day Off | 0 | 0
| Inclement |  |  |  | No | [8 empty] | Inclement Weather Day | 0 | 0
| n/a | / | n/a | / | n/a | [8 empty] | Break Check | 0
Phase Break or Winter Shutdown | [13 empty] | Site Occupancy Cycle Count |  | 0
Inclement Weather Day Summary | [5 empty] | Lane Closure Summary |  |  |  | Site Occupancy Day Summary |  |  |  |  | 0
This Week: |  |  | 0 |  |  | This Week: |  |  | 0 | This Week: | 0 |  |  |  | N/A
Brought Forward: |  |  | 0 |  |  | Brought Forward: |  |  | 0 | Brought Forward: | 0 |  |  |  | 0
Total to Date: |  |  | 0 |  |  | Total to Date: |  |  | 0 | Total to Date: | 0
[6 empty] | Total Lanes Bid: |  |  | 0 | Total Days Bid: | 0
[6 empty] | Additional Lanes Approved: |  |  | 0 | Additional Days Approved: | 0
[6 empty] | Penalty Assessment: |  |  |  | Penalty Assessment:
Contractor's Comments:
Contractor's Signature: | [9 empty] | Consultant's Signature:
Site Occupancy Count Total / Pre Scheduled Day Off Count out of 8 / Day Number in 30 Day Cycle
Revised July 2016 | [10 empty] | Appendix A.07
Note on M27: Enter: Highway and Control Section or Bridge File Number
Note on L29: Enter: Consultant/Inspector Name
Note on G33: Enter: Yes or No
Note on G34: Enter: Yes or No
Note on G35: Enter: Yes or No
Note on G39: Enter: Yes or No
Note on G40: Enter: Yes or No
Note on G41: Enter: Yes or No
Note on G45: Enter: Yes or No
Note on G46: Enter: Yes or No
Note on G47: Enter: Yes or No
Note on G51: Enter: Yes or No
Note on G52: Enter: Yes or No
Note on G53: Enter: Yes or No
Note on G57: Enter: Yes or No
Note on G58: Enter: Yes or No
Note on G59: Enter: Yes or No
Note on G63: Enter: Yes or No
Note on G64: Enter: Yes or No
Note on G65: Enter: Yes or No
Note on G69: Enter: Yes or No
Note on G70: Enter: Yes or No
Note on G71: Enter: Yes or No

## Sample
Weekly Data: | [12 empty] | Project Data: | [6 empty] | Labour Data:
Weekly Progress Report Number | [5 empty] | 2 | Enter: Last Week's Weekly Progress Number
(Last Week): | [19 empty] | Labour Data Summary - Consultant
[21 empty] | Brought Forward | This Week | Total to Date
Site Occupancy Days Tracking | [12 empty] | Site Occupancy Days | [6 empty] | Total Number of Staff Days | 40 | 30 | 70 | Enter: Total Number of staff days on this Contract this week
Site Occupancy Days | [5 empty] | 14 | Enter: Number of Site Occupancy Days Used to Date | [5 empty] | Total Days Bid: | 10 | Enter: Project Total Number of Site Occupancy Days Bid |  |  |  |  | Example: 5 staff per day times 6 days this week = 30 staff days per week |  |  |  | This includes office, aggregate and on-site field staff
(Brought Forward): | [12 empty] | Additional Days Approved: | 5 | Enter: Additional Number of Site Occupancy Days Approved
Site Occupancy 30 Day Cycle | [5 empty] | 27 | Enter: Day Number in 30 Day Cycle Brought Forward (as of last report) | [5 empty] | Unit Price: | 800 | Enter: Unit Price from Unit Price Schedule |  |  |  |  | Labour Data Summary - Contractor
(Brought Forward): | [20 empty] | Brought Forward | This Week | Total to Date
Pre Scheduled Days Off Cycle | [5 empty] | 3 | Enter: Number of Pre Scheduled Days Off Used to Date in 8 Day Cycle | [12 empty] | Total Number of Staff Days | 40 | 60 | 100 | Enter: Total Number of staff days on this Contract this week
(Brought Forward): | [19 empty] | Example: 10 staff per day times 6 days this week = 60 staff days per week |  |  |  | This includes office, aggregate, on-site field staff
Inclement Weather Days | [5 empty] | 5 | Enter: Number of Inclement Days Brought Forward (as of last report)
(Brought Forward):
Lane Closure Tracking | [12 empty] | Lane Closure
Lane Closures | [5 empty] | 8 | Enter: Number of Lane Closures Brought Forward (as of last report) | [5 empty] | Total Lanes Bid: | 9 | Enter: Project Total Number of Lane Closures Bid
(Brought Forward): | [12 empty] | Additional Lanes Approved: | 3 | Enter: Additional Number of Lane Closures Approved
Lane Closures | [5 empty] | 6 | Enter: Number of Lane Closures This Week | [5 empty] | Unit Price: | 500 | Enter: Unit Price from Unit Price Schedule
(This Week):
[5 empty] | Site Occupancy and Lane Closure Weekly | [6 empty] | Report # 3
Project: | Hwy 999 over Big River | [6 empty] | Hwy #:CS or Bridge File: |  |  | BF 99999 | [6 empty] | 14 | Site Occupancy Days (Brought Forward)
Contractor: | XYZ Construction | [6 empty] | Contract Number: |  |  | 10999 | [6 empty] | 3 | Pre Scheduled 8 Days Off Cycle (Brought Forward)
Week Ending: | 2013-10-05 | [6 empty] | Consultant: |  | ABC Consulting / John Doe | [7 empty] | 5 | Inclement Weather Days (Brought Forward)
DATE & DAY | [5 empty] | DAILY PROGRESS AND COMMENTS | [11 empty] | 27 | Site Occupancy 30 Day Cycle (Last Week)
2013-09-29 | [16 empty] | This Week | Total to Date
Weather | SO Day |  |  |  | No | [10 empty] | Site Occupancy | 0 | 14
Sunny | Day Off |  |  |  | Yes | [10 empty] | Pre Scheduled Day Off | 1 | 4
High +10°C | Inclement |  |  |  | No | [10 empty] | Inclement Weather Day | 0 | 5
Low -1°C | 14 | / | 4 | / | 28 | [10 empty] | Break Check | 1 |  | If Zero, Project is on Preschedule Phase Break or Winter Shutdown
------------------- | [10 empty] | Lane Closures this day: 1 |  |  |  |  | Site Occupancy Cycle Count |  | 28 | Tracking of 30 Day Cycle
2013-09-30
Weather | SO Day |  |  |  | Yes | Placing rebar centre pier | [9 empty] | Site Occupancy | 1 | 15
Overcast | Day Off |  |  |  | No | Closed right lane for rebar delivery | [9 empty] | Pre Scheduled Day Off | 0 | 4
High +15°C | Inclement |  |  |  | No | Wind 15 km/h SE | [9 empty] | Inclement Weather Day | 0 | 5
Low -1°C | 15 | / | 4 | / | 29 | [10 empty] | Break Check | 1
------------------- | [5 empty] | Crew: 8 |  |  |  |  | Lane Closures this day: 2 |  |  |  |  | Site Occupancy Cycle Count |  | 29
2013-10-01
Weather | SO Day |  |  |  | No | Site shutdown at 10:00 due to rain | [9 empty] | Site Occupancy | 0 | 15
Raining | Day Off |  |  |  | No | [10 empty] | Pre Scheduled Day Off | 0 | 4
High +9°C | Inclement |  |  |  | Yes | [10 empty] | Inclement Weather Day | 1 | 6
Low +1°C | 15 | / | 4 | / | 30 | [10 empty] | Break Check | 1
------------------- | [10 empty] | Lane Closures this day: 1 |  |  |  |  | Site Occupancy Cycle Count |  | 30
2013-10-02
Weather | SO Day |  |  |  | Yes | Forming and placing rebar at centre pier | [9 empty] | Site Occupancy | 1 | 16
Sunny | Day Off |  |  |  | No | Closed right lane for formwork installation | [9 empty] | Pre Scheduled Day Off | 0 | 0
High +1°C | Inclement |  |  |  | No | Placed abutment 1 grade beam concrete | [9 empty] | Inclement Weather Day | 0 | 6
Low -10°C | 16 | / | 0 | / | 1 | Heating and hoarding of grade beam | [9 empty] | Break Check | 1
------------------- | [10 empty] | Lane Closures this day: 2 |  |  |  |  | Site Occupancy Cycle Count |  | 1
2013-10-03
Weather | SO Day |  |  |  | Yes | Heating and hoarding of grade beam | [9 empty] | Site Occupancy | 1 | 17
Sunny | Day Off |  |  |  | No | [10 empty] | Pre Scheduled Day Off | 0 | 0
High -5°C | Inclement |  |  |  | No | [10 empty] | Inclement Weather Day | 0 | 6
Low -15°C | 17 | / | 0 | / | 2 | [10 empty] | Break Check | 1
------------------- | [15 empty] | Site Occupancy Cycle Count |  | 2
2013-10-04
Weather | SO Day |  |  |  | Yes | Heating and hoarding of grade beam | [9 empty] | Site Occupancy | 1 | 18
Sunny | Day Off |  |  |  | Yes | [10 empty] | Pre Scheduled Day Off | 1 | 1
High -13°C | Inclement |  |  |  | No | [10 empty] | Inclement Weather Day | 0 | 6
Low -22°C | 18 | / | 1 | / | 3 | [10 empty] | Break Check | 2
Review Site Occupancy Inputs | [5 empty] | Crew: 6 | [9 empty] | Site Occupancy Cycle Count |  | 3
2013-10-05
Weather | SO Day |  |  |  | No | Project shutdown for winter | [9 empty] | Site Occupancy | 0 | 18
| Day Off |  |  |  | No | [10 empty] | Pre Scheduled Day Off | 0 | 1
| Inclement |  |  |  | No | [10 empty] | Inclement Weather Day | 0 | 6
| n/a | / | n/a | / | n/a | [10 empty] | Break Check | 0
Phase Break or Winter Shutdown | [15 empty] | Site Occupancy Cycle Count |  | --
Inclement Weather Day Summary | [5 empty] | Lane Closure Summary |  |  |  | Site Occupancy Day Summary | [5 empty] | Site Occupancy | 4
This Week: |  |  | 1 |  |  | This Week: |  |  | 6 | This Week: |  | 4 |  |  |  | Pre Scheduled Day Off | N/A
Brought Forward: |  |  | 5 |  |  | Brought Forward: |  |  | 8 | Brought Forward: |  | 14 |  |  |  | Inclement Weather Day | 1
Total to Date: |  |  | 6 |  |  | Total to Date: |  |  | 14 | Total to Date: |  | 18
[6 empty] | Total Lanes Bid: |  |  | 9 | Total Days Bid: |  | 10
[6 empty] | Additional Lanes Approved: |  |  | 3 | Additional Days Approved: |  | 5
[6 empty] | Penalty Assessment: |  |  | 1000 | Penalty Assessment: |  | 2400
Contractor's Comments:
Contractor's Signature: | [9 empty] | Consultant's Signature:
Site Occupancy Count Total / Pre Scheduled Day Off Count out of 8 / Day Number in 30 Day Cycle
Revised July 2016 | [11 empty] | Appendix A.07
SAMPLE
Note on M27: Enter: Highway and Control Section or Bridge File Number
Note on L29: Enter: Consultant/Inspector Name
Note on G33: Enter: Yes or No
Note on G34: Enter: Yes or No
Note on G35: Enter: Yes or No
Note on G39: Enter: Yes or No
Note on G40: Enter: Yes or No
Note on G41: Enter: Yes or No
Note on G45: Enter: Yes or No
Note on G46: Enter: Yes or No
Note on G47: Enter: Yes or No
Note on G51: Enter: Yes or No
Note on G52: Enter: Yes or No
Note on G53: Enter: Yes or No
Note on G57: Enter: Yes or No
Note on G58: Enter: Yes or No
Note on G59: Enter: Yes or No
Note on G63: Enter: Yes or No
Note on G64: Enter: Yes or No
Note on G65: Enter: Yes or No
Note on G69: Enter: Yes or No
Note on G70: Enter: Yes or No
Note on G71: Enter: Yes or No

## Sheet1 (hidden)
Yes
No