## CIR compaction report
DAILY COMPACTION REPORT - Cold In-Place Recycling (CIR)
|  |  | CONTRACT NO. |  |  |  | PROJECT NO. |  |  | CONTRACTOR |  |  | PRIME CONSULTANT
|  |  | PROJECT FROM |  |  |  | PROJECT TO |  |  | DESIGN PROCTOR |  |  | QA CONSULTANT
kg/m3
CIR1/12
CIR MIX |  |  |  | CIR PAVEMENT
DATE SAMPLED | LOT NO. |  | MOISTURE | DATE SAMPLED |  | LOT NO. | LANE | STATION | OFFSET |  | SLAB |  | SLAB |  | COMPACTION
|  | DENSITY | CONTENT | [7 empty] | DENSITY |  | MOISTURE
|  | kg/m3 | % | [5 empty] | m |  | kg/m3 |  | % |  | %
Lot Average
COMMENTS: |  |  |  | Lot No. | Lane | From | To | Area (m2) | TECHNOLOGISTS:
PROJECT MANAGER:
RECEIVED BY:
[6 empty] | TYPE |  | AMOUNT |  |  |  | *** Contractors Representative
%
BITUMINOUS STABILIZING ADDITIVE
[9 empty] | DATE RECEIVED: |  |  |  |  | TIME:
CEMENT ADDITIVE
*** Signature indicates receipt of data on the date and time indicated
Revised December 2013 | [15 empty] | Appendix B.14

## CIR compaction Sample
DAILY COMPACTION REPORT - Cold In-Place Recycling (CIR)
|  |  | CONTRACT NO. | 123654 |  |  | PROJECT NO. | Hwy XX:xx |  | CONTRACTOR |  |  | PRIME CONSULTANT
|  |  | PROJECT FROM |  |  |  | PROJECT TO |  |  | DESIGN PROCTOR |  |  | QA CONSULTANT
[10 empty] | 2065 |  | kg/m3
CIR1/12
CIR MIX |  |  |  | CIR PAVEMENT
DATE SAMPLED | LOT NO. | MARSHALL | MOISTURE | DATE SAMPLED |  | LOT NO. | LANE | STATION | OFFSET |  | SLAB |  | SLAB |  | COMPACTION
|  | DENSITY | CONTENT | [7 empty] | DENSITY |  | MOISTURE
|  | kg/m3 | % | [5 empty] | m |  | kg/m3 |  | % |  | %
2012-06-18 | 12 | 2105 | 4.8 | 2012-06-29 |  | 12 | EBL | 16+120 | 2.1 rt |  | 2110 |  | 2.2 |  | 100.3
2012-06-18 | 12 | 2100 | 5 | 2012-06-29 |  | 12 | EBL | 16+905 | 3.0 rt |  | 2101 |  | 1.9 |  | 99.9
2012-06-18 | 12 | 2106 | 4.1 | 2012-06-29 |  | 12 | EBL | 17+504 | 2.2 rt |  | 2097 |  | 1.9 |  | 99.7
Lot Average |  | 2103.6667 | 4.6333 | [7 empty] | 2102.6667 |  | 2 |  | 99.9667
COMMENTS: |  |  |  | Lot No. | Lane | From | To | Area (m2) | TECHNOLOGISTS:
Lot 12 CIR has sufficiently cured for ACP placement. |  |  |  | 12 | EBL | 15+910 | 17+605 | 6272
PROJECT MANAGER:
RECEIVED BY:
[6 empty] | TYPE |  | AMOUNT |  |  |  | *** Contractors Representative
%
|  |  |  | BITUMINOUS STABILIZING ADDITIVE |  | CRS-2 |  | 1.4
[9 empty] | DATE RECEIVED: |  |  |  |  | TIME:
|  |  |  | CEMENT ADDITIVE |  | GU |  | 1
*** Signature indicates receipt of data on the date and time indicated
Revised December 2013 | [15 empty] | Appendix B.14
SAMPLE