## C.10
CULVERT INSTALLATION
Inspection Record
Project: |  |  | Contract #: |  |  | Bridge File
Contractor:
Project Sponsor: |  |  |  |  | Consultant Inspector:
STRUCTURAL | DESIGNATION |  | SOURCE |  | TESTED BY |  | APPROVED BY
FILL | REQUIRED
Granular Fill | Des 2 - Class 20 or
Crush | Des 2 - Class 40
Pit run | Des 6 - Class 80
Clay Fill
INSTALLATION |  | INSPECTED BY |  | DATE |  | COMMENTS
Culvert Settings
Excavation
Bedding
Assembly
Backfill
Haunch Area
Sidewall Area
COMPACTION
EQUIPMENT
Lift Thickness |  |  | mm |  | Passes per Lift
CONCRETE END TREATMENT |  | INSPECTED BY |  | DATE |  | COMMENTS
Rebar and Formwork
Finished Work
Concrete Compressive Strength
Riprap
Special Features
Final Trimming/Cleanup
Please return form to Project Sponsor
Revised December 2013 | [7 empty] | Appendix C.10

## C.10 sample
CULVERT INSTALLATION
Inspection Record
Project: | Hwy XX:xx |  | Contract #: | CON00123456 |  | Bridge File #: | 12345
Contractor:
Project Sponsor: |  |  |  |  | Consultant Inspector:
STRUCTURAL | DESIGNATION |  | SOURCE |  | TESTED BY |  | APPROVED BY
FILL | REQUIRED
Granular Fill | Des 2 - Class 20 or |  | Borrow, or pit |  | Geotech Sub -cons |  | Prime Consultant
Crush | Des 2 - Class 40 |  | Borrow, or pit |  | Geotech Sub -cons |  | Prime Consultant
Pit run | Des 6 - Class 80 |  | Borrow, or pit |  | Geotech Sub -cons |  | Prime Consultant
Clay Fill |  |  | Borrow, or pit |  | Geotech Sub -cons |  | Prime Consultant
INSTALLATION |  | INSPECTED BY |  | DATE |  | COMMENTS
Culvert Settings |  | inspector |  | date |  | camber and inverts per design,
Excavation |  | inspector |  | date |  | firm , competent, no additional
Bedding |  | inspector |  | date |  | per design, no issues
Assembly |  | inspector |  | date |  | minor issues with hole alignment
Backfill |  | inspector |  | date |  | oversize cobbles removed
Haunch Area |  | inspector |  | date |  | hand tamped in corrugation
Sidewall Area |  | inspector |  | date |  | no issues
COMPACTION
EQUIPMENT | Sheep foot roller, jumping jack, hand plate tamper
Lift Thickness | 150 |  | mm |  | Passes per Lift |  | 6
CONCRETE END TREATMENT |  | INSPECTED BY |  | DATE |  | COMMENTS
Rebar and Formwork |  | inspector |  | date |  | min cover provided, per std. dwgs.
Finished Work |  | inspector |  | date |  | finished and covered for cure
Concrete Compressive Strength |  | inspector |  | date |  | # cylinders & date, check lab
Riprap |  | inspector |  | date |  | per spec, gradation good, cloth in
Special Features |  | inspector |  | date |  | sideslope handrail in place
Final Trimming/Cleanup |  | inspector |  | date |  | erosion control still in place.
Please return form to Project Sponsor
Revised December 2013 | [7 empty] | Appendix C.10
SAMPLE