## Form D.04
CHECKING FINAL DETAILS
***** GRADING CHECKLIST *****
Project: |  | WAC/Job:
CONTRACTOR: |  | Contract No.:
CONSULTANT: |  | Region:
|  | Checked |  | Corrections
|  | Completed By | Date | Req'd | Completed By | Date
ü | 1. CROSS SECTIONS
- Are all stations present? (check volumes report)
- Are all applicable surfaces present? (check XNG files & Panel 2)
- Survey data checked for errors? (H.I. values, rod reading errors)
- Are the surface to surface tie-ins correct? (e.g. vertical vs. sloped)
- Are common and borrow separated at right-of-way boundaries?
- Digital Terrain Modeling done correctly?
- Are cross sections extracted correctly? (e.g. correct alignment used, etc.)
2. AREAS
- Are the area parameters set correctly? (Panel 2)
- Are the areas coloured correctly? (no overlaps or doubling)
- Is the Undercut calculated correctly?
- Are the areas matching the volumes report? (random check)
- Do the area values seem reasonable?
3. VOLUMES
- Volume reports completed? (main align., borrow pits, R/A's, etc.)
- Are all "Point Volumes" included & documented? (apps., piles, culverts, etc.)
- Are volumes summarized and totaled?
- Are "Remove & Replace" quantities accounted for? (B.T.S. , Topsoil, culverts, etc. - doubled or measured twice)
- Are quantities for Channel Exc. measured & calculated correctly?
4. OVERHAUL
- Are the "Code Point" files correct? (station, quantity, dead haul, etc.)
- Are the "Haul Quantity" files correct?
- Are all "Accumulated Sum" files correct?
- Are the Overhaul summaries correct?
- Are all Overhaul diagrams correct?
5. FINAL DETAILS SHEETS
- Are numbers correctly transferred from original data?
- Are all items measured and recorded (i.e. field books)?
- Are all calculations and totals correct?
- Are Final Details completed as per Section 5?
6. BORROW PITS
- Are borrow Pits plans completed and correct?
- Is Information for Reclamation Certificates included?
- Are the Pre-Construction Assessments included?
NOTE: This checklist is intended to be a guide and/or a reminder. It has been
| developed with EMXS in mind, however the logical steps can be applied to other |  | Certified Correct by:
earthwork software packages. The checking process requires more detail than
| indicated above and it is the responsibility of the checker to ensure the final |  |  | Date:
details are thoroughly checked.
For Consultant's Internal Use. Submit copy to Region ONLY.