## Form D.13a
FINAL DETAILS
Bid Item Details
Area Based Measurements
WAC/Job No.: |  |  | PROJECT:
Contract No.: |  |  | CONTRACTOR:
REGION:
Bid Item | #___ | , Description
STATION TO STATION | L/R/C | LENGTH (m) | WIDTH (m) | AREA (m2) | REMARKS
TOTAL |  |  |  | 0
Bid Item | #___ | , Description
STATION TO STATION | L/R/C | LENGTH (m) | WIDTH (m) | AREA (ha) | REMARKS
TOTAL |  |  |  | 0
This form is to be used for area measurements:
Clearing, seeding, top soiling, subgrade prep, prime
coat, tack coat, fog coat, fog coat seal, etc. |  |  |  | Certified Correct

## FormD.13b
FINAL DETAILS
Bid Items - Area Based Measurement
Bid Item X, Include Description
WAC/Job No.: |  |  | PROJECT:
Contract No.: |  |  | CONTRACTOR:
REGION:
STATION TO STATION |  | LENGTH | WIDTH | AREA | REMARKS
| L/R/C | m | m | m²
TOTAL
This form is to be used for area measurements:
Clearing, seeding, topsoiling, subgrade prep, prime |  |  |  | Certified Correct
coat, tack coat, fog coat, fog coat seal, etc.

## D.13 - Sample
FINAL DETAILS
Bid Item Details
Area Based Measurements
WAC/Job No.: | WAC xxxxxxx |  |  | PROJECT: | Hwy XX:xx (km 16.77.12 to 34.12)
Contract No.: |  |  |  | CONTRACTOR:
REGION:
Bid Item 4, Cold Milling Asphalt Pavement
STATION TO STATION |  | L/R/C | LENGTH (m) | WIDTH (m) | AREA (m2) | REMARKS
34130 | 25140 | R | 8990 | 3.8 | 34162 | May 11-13
25140 | 16765 | R | 8375 | 3.8 | 31825 | May 12-13
16765 | 24000 | L | 7235 | 4 | 28940 | May 13-13
24000 | 32455 | L | 8455 | 4 | 33820 | May 14-13
32455 | 34130 | L | 1675 | 4 | 6700 | May 15-13
TOTAL |  |  |  |  | 135447
Bid Item 6, Supply and Place Fog Coat
STATION TO STATION |  | L/R/C | LENGTH (m) | WIDTH (m) | AREA (m2) | REMARKS
34120 | 27783 | R | 6337 | 2.45 | 15525.7 | May 17-13, NB Lane
27783 | 18545 | R | 9238 | Varies | 22633.1 | May 18-13, NB Lane
34120 | 23755 | L | 10365 | 2.55 | 26430.8 | May 19-13, SB Lane
23755 | 18711 | L | 5044 | 2.55 | 12862.2 | May 20-13, SB Lane
18545 | 16770 | R | 1775 | Varies | 4348.8 | May 25-13, NB Lane
18711 | 16770 | L | 1941 | 2.55 | 4949.6 | May 25-13, SB Lane
TOTAL |  |  |  |  | 86750.2
This form is to be used for area measurements:
Clearing, seeding, topsoiling, subgrade prep, prime
coat, tack coat, fog coat, fog coat seal, etc. |  |  |  |  | Certified Correct
SAMPLE