## Tender List
Projects on this list are expected to be tendered for Fiscal Year 2026/2027 construction based on the Department's best information at the time of publishing, and are subject to change.
Material Quantities are approximate and not available for all tenders and work activities. The material estimates may be pre-tender and are subject to change.
Scheduled years may change with the publishing of a new construction program each spring.
Region | Tender Number | Estimated Tender Construction Value | Scheduled Year | Highway | Work Description | Length | Type of Work | Estimated ACP (Tonnes, rounded to nearest 1000) | Estimated GBC (Tonnes, rounded to nearest 1000) | Estimated Earth (Cubic Meters, rounded to nearest 1000)
CENTRAL | TND0015522 | $ | 2026 | 734 | 734:16 Elk Creek Bridge on Hwy 734, 69 Km S of Nordegg (77585-1)(77585-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
CENTRAL | TND0020172 | $ | 2026 | 11 | 11:10 Watercourse Culvert on Provincial Highway 11 near Rocky Mt Hou (9499-1) (Bridge Bundle)(9499-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
CENTRAL | TND0021533 | $ | 2026 | 791 | 791:08 Spruce Creek Bridge on Provincial Highway 791 near Olds (75422-1)(75422-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
CENTRAL | TND0021616 | $ | 2026 | 36 | 36:12 Castor Creek Culvert on Provincial Highway 36 near Castor (75734-1)(75734-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
CENTRAL | TND0021892 | $ | 2026 | 580 | 580:02 Beaverdam Creek Bridge on Provincial Highway 580 near Carstairs (433-1) (Bridge Bundle)(433-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
|  |  |  | 734 | 734:16 Otter Creek Bridge on Provincial Highway 734 near Nordegg (77589-1) (Bridge Bundle)(77589-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
CENTRAL | TND0021894 | $$ | 2026 | 897 | 897:06 Vermilion River Bridge on Highway 897, 16 Km N of Marwayne (1916-1)(1916-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 6000 | 10000 | 100000
CENTRAL | TND0022696 | $ | 2026 | 584 | 584:02 Replacement of Tributary to James River Culvert (BF 83247)(83247-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
CENTRAL | TND0025459 | $$ | 2026 | 10X | 10X:02 Rosebud River Bridge on Highway 10x, 1 Km S of Rosedale (70510-1)(70510-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
CENTRAL | TND0025457 | $$ | 2026 | 11 | 11:16 Hwy 815 - 10 Km W of Hwy 921(11:16 C1 0.000 - 9.800) | 9.8 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 17000 | 0 | 0
|  |  |  | 821 | 821:02 6 Km S of Hwy 605 - Hwy 605(821:02 C1 6.600 - 12.800) | 6.2 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 7000 | 1000 | 0
|  |  |  | 42 | 42:08 Hwy 816 - Hwy 21(42:08 C1 25.755 - 44.019) | 18.264 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 20000 | 0 | 0
|  |  |  | 815 | 815:02 Hwy 11 - Hwy 597(815:02 C1 0.000 - 7.518) | 7.518 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 11000 | 0 | 0
|  |  |  | 595 | 595:02 CITY of Red Deer - Hwy 808(595:02 C1 0.000 - 9.926) | 9.926 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 18000 | 1000 | 0
CENTRAL | TND0021637 | $$$$ | 2026 | 11 | 11:10 Hwy 11:10 Twinning - Town of Rocky Mountain House to 1 Km E of Hwy 22 (Economic Recovery)(11:10 C1 11.547 - 18.464) | 6.917 | TWINNING - GRADE, BASE, 1ST STAGE PAVING | 74000 | 187000 | 335000
CENTRAL | TND0023734 | $$$$ | 2026 | 13 | 13:20 Hwy 899 - 16 Km E of TOWN of Provost(13:20 C1 44.895 - 60.985) | 16.09 | OVERLAY | 60000 | 10000 | 25000
|  |  |  | 13 | 13:20 Hwy 13:20, new intersection at Service Road - km 45.449(13:20 C1 44.949 - 45.949) | 1 | INTERSECTION IMPROVEMENT | 2000 | 7000 | 16000
|  |  |  | 41 | 41:14 PAR 121 - 4 Km N of Hwy 600(41:14 C1 12.800 - 41.756) | 28.956 | OVERLAY | 96000 | 14000 | 38000
|  |  |  | 600 | 600:02 16 Km W of Hwy 13 - Hwy 13(600:02 C1 26.766 - 42.497) | 15.731 | OVERLAY | 40000 | 3000 | 0
CENTRAL | TND0024176 | $$ | 2026 | 16 | 16:30 9 km E of Hwy 897 – City of Lloydminster(16:30 R1 45.540 - 55.154) | 9.614 | OVERLAY | 35000 | 3000 | 17000
CENTRAL | TND0024337 | $$$$ | 2026 | 855 | 855:16 TOWN of Mundare - Hwy 29(855:16 C1 0.000 - 20.585) | 20.585 | OVERLAY | 38000 | 17000 | 55000
|  |  |  | 15 | 15:08 Hwy 15:08 Rehabilitation - Mundare to Hwy 16(15:08 C1 44.890 - 47.103) | 2.213 | OVERLAY | 6000 | 1000 | 0
|  |  |  | 857 | 857:04 Hwy 16A - Hwy 45(857:04 C1 0.000 - 33.680) | 33.68 | OVERLAY | 75000 | 4000 | 3000
CENTRAL | TND0024488 | $ | 2026 | 595 | 595:02 Upgrade Intersection to Type IIIa - Int of Hwy 595:02 and Range Road 262 (E of Red Deer)(20370-) | 0 | INTERSECTION IMPROVEMENT | 2000 | 5000 | 17000
CENTRAL | TND0024580 | $$$ | 2026 | 11 | 11:12 Hwy 11:12 Grading - 1 Km E of Hwy 766 to 1 Km E of Benalto (Economic Stimulus) (11:12 C1 0.300 - 7.540) | 7.24 | GRADING | 0 | 0 | 388000
CENTRAL | TND0024702 | $$ | 2026 | 607 | 607:02 Hwy 761 - Hwy 20(607:02 C1 0.000 - 17.784) | 17.784 | OVERLAY | 47000 | 1000 | 14000
CENTRAL | TND0025114 | $ | 2026 | 841 | 841:02 Slide repair on 841:02 (C012)(841:02 C1 5.000 - 8.000) | 3 | SLIDE REPAIR | 0 | 0 | 1000
CENTRAL | TND0025580 | $$ | 2026 | VARIOUS | VARIOUS: 2026 Central Region Seal Coat Program |  | CHIP SEAL | 0 | 0 | 0
CENTRAL | TND0025610 | $$ | 2026 | 587 | 587:02 7 Km E of Hwy 766 - 10 Km E of Hwy 766(587:02 C1 28.791 - 31.100) | 2.309 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 3000 | 0 | 0
|  |  |  | 27 | 27:06 TOWN of Olds - Hwy 2 selective(27:06 C1 36.240 - 36.640; 27:06 C1 38.135 - 43.980; 27:06 L1 36.640 - 38.135; 27:06 R1 36.640 - 38.133) | 9.233 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 17000 | 1000 | 0
|  |  |  | 27 | 27:06 Turning lanes on Hwy 27 for RR23 (MLA List Project)(10397-) | 0 | INTERSECTION IMPROVEMENT | 2000 | 2000 | 0
|  |  |  | 839 | 839:02 Hwy 27 - Hwy 585(839:02 C1 0.000 - 22.738) | 22.738 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 28000 | 2000 | 0
NORTH CENTRAL | TND0012552 | $$$$$ | 2026 | 60 | 60:02,04 Capital Improvements over CNR (between Hwy 16 & 16A)(60:02 L1 31.743 - 32.144; 60:04 C1 0.676 - 1.947; 60:04 L1 0.000 - .676; 60:04 L1 1.947 - 3.644) | 4.045 | TWINNING - GRADE, BASE, 1ST STAGE PAVING | 84000 | 102000 | 994000
|  |  |  | 60 | 60:04 Highway 60 Over CNR (new Structures) - Stage 1(78729-1) | 0 | TWINNING - STRUCTURE | 0 | 0 | 0
|  |  |  | 16A | 16A:16 Highway 60 Over Highway 16A Interchange (new NBL structure)(77521-3) | 0 | INTERCHANGE - BRIDGE STRUCTURE | 0 | 0 | 0
|  |  |  | 16A | 16A:16 Highway 16A and 60 Interchange New Roadwork Construction(98-) | 0 | INTERCHANGE UPGRADING | 15000 | 27000 | 321000
|  |  |  | 16A | 16A:16 Highway 60 Over Highway 16A (SBL Structure Modifications)(77521-1) | 0 | INTERCHANGE - BRIDGE STRUCTURE | 0 | 0 | 0
NORTH CENTRAL | TND0018555 | $ | 2026 | 777 | 777:01 Sturgeon River Bridge on Provincial Highway 777 near Onoway (7484-1)(7484-1) | 0 | REPLACE BRIDGE(CONCRETE CULVERT OR SPAN STRUCTURE ONLY) | 0 | 0 | 0
NORTH CENTRAL | TND0019347 | $ | 2026 | 22 | 22:30 Watercourse Culvert on Provincial Highway 22 near Rocky Rapids (74367-1)(74367-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0019894 | $ | 2026 | 778 | 778:02 Weed Creek Bridge on Highway 778, At Thorsby (7750-1)(7750-1) | 0 | BRIDGE DECK WATERPROOFING SYSTEM | 0 | 0 | 0
NORTH CENTRAL | TND0021565 | $ | 2026 | 33 | 33:04 25 km N of Gunn (NC010-1)(33:04 C1 25.005 - 25.006) | 0.001 | SLIDE REPAIR | 0 | 0 | 0
NORTH CENTRAL | TND0023150 | $ | 2026 | 621 | 621:02 Watercourse Culvert on Provincial Highway 621 near Easyford (74956-1)(74956-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0023151 | $ | 2026 | 759 | 759:02 Watercourse Culvert on Provincial Highway 759 near Berrymoor (71003-1)(71003-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0023184 | $ | 2026 | 32 | 32:10 Watercourse Culvert on Provincial Highway 32, 19 Km SW of Whitecourt (1674-1)(1674-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0023186 | $ | 2026 | SHERWOOD PARK FREEWAY | SHERWOOD PARK FREEWAY:02 Watercourse Culvert on Sherwood Park Freeway, In Edmonton (76423-1)(76423-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0023943 | $ | 2026 | 624 | 624:02 NC057 Settlement Repair (624:02 C1 2.500 - 2.510)(624:02 C1 2.500 - 2.510) | 0.01 | SLIDE REPAIR | 0 | 0 | 0
NORTH CENTRAL | TND0024993 | $ | 2026 | 754 | 754:06 NC110 - Hwy 754:06 Wabasca Lake Slip N' Slide Repairs(754:06 C1 32.939 - 32.940) | 0.001 | SLIDE REPAIR | 0 | 0 | 0
NORTH CENTRAL | TND0020252 | $$$$ | 2026 | 881 | 881:21 Safety and Roadway Improvements - NB/SB passing and climbing lanes, service roads and NB SRA/TSA on Hwy 881:21(881:21 C1 19.400 - 22.600; 881:21 C1 30.470 - 36.320; 881:21 C1 37.400 - 39.620; 881:21 C1 44.600 - 47.350) | 14.02 | CLIMBING LANE | 91000 | 181000 | 709000
NORTH CENTRAL | TND0023658 | $ | 2026 | 16A | 16A:14 Intersection Improvement - Hwy 16A/RR20 (Lake Eden Road)(754-) | 0 | INTERSECTION IMPROVEMENT | 0 | 0 | 0
NORTH CENTRAL | TND0024290 | $$$$$ | 2026 | 63 | 63:12 Beaver River Culvert on Provincial Highway 63 near Fort Mackay (77557-1)(77557-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 1000
|  |  |  | 63 | 63:12 Hwy63:12-Mildred Lake North Gate to South of Peter Lougheed Bridge(km 39.825 to km 46.955)(63:12 C1 39.825 - 46.354; 63:12 L1 46.354 - 46.955) | 7.13 | TWINNING - GRADE, BASE, 1ST STAGE PAVING | 92000 | 227000 | 1470000
|  |  |  | 63 | 63:12 Bridge Creek Culvert on Provincial Highway 63 near Fort Mackay (78105-1)(78105-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
NORTH CENTRAL | TND0022344 | $$$ | 2026 | 2 | 2:30 Highway 2 Over Highway 39 Interchange, At Leduc (75055-2)(75055-2) | 0 | DECK REPLACEMENT | 0 | 0 | 0
|  |  |  | 2 | 2:30 Highway 2 Over Highway 39 Interchange, At Leduc (75055-1)(75055-1) | 0 | DECK REPLACEMENT | 0 | 0 | 0
NORTH CENTRAL | TND0012201 | $$$$$ | 2026 | 2 | 2:36 Cardiff Road Near Morinville, BF85214 | 0 | INTCH-ST
|  |  |  | 2 | 2:36 Interchange at Cardiff Road South of Morinville (inc. realignment, km 5.75 to 9.357) | 0 | INTCH-GBP | 58000 | 109000 | 1400000
NORTH CENTRAL | TND0020479 | $$$$$ | 2026 | 40 | 40:30,32 S of Pinto Creek - N of Berland R (40:30 C1 54.900 - 57.060; 40:32 C1 9.400 - 25.200) | 0 | GWI | 66000
|  |  |  | 40 | 40:32 Berland River Bridge, 62 Km N. of Entrance (74710-1) | 0 | BRIDGE-REPLACE
|  |  |  | 40 | 40:32 Tributary to Fox Creek, 67 Km NW of Hinton (77196-1) | 0 | BRIDGE-S-CULVERT
|  |  |  | 40 | 40:30 Pinto Creek Culvert near Entrance (77194-1) | 0 | BRIDGE-S-CULVERT
|  |  |  | 40 | 40:30 Watercourse Culvert near Entrance (77193-1) | 0 | BRIDGE-S-CULVERT
|  |  |  | 40 | 40:32 Safety Rest Area NC-028C (NBL) S of Muskeg Cabins (40:32 C1 15.560 - 16.300) | 0 | SAFETY REST AREA
NORTH CENTRAL | TND0024494 | $$$ | 2026 | 28 | Hwy 28:08 – UAR 104 to Hwy 36 |  | OVERLAY | 123000
|  |  |  | 28 | UAR 156:02 – Hwy 28 to 1 km S of Hwy 28 |  | OVERLAY | 1600
PEACE | TND0023853 | $$ | 2026 | 43 | 43:12 Iosegun River Bridge on Highway 43, 17 Km SE of Fox Creek (73921-1)(73921-1) | 0 | DECK REPLACEMENT | 4000 | 4000 | 12000
|  |  |  | 43 | 43:08 Little Smoky River Bridge on Provincial Highway 43, At NW Boundary of Little Smoky (73836-1)(73836-1) | 0 | BRIDGE DECK CONCRETE OVERLAY | 0 | 0 | 0
PEACE | TND0025709 | $ | 2026 | 750 | 750:02 Lesser Slave River Bridge on Highway 750, 1 Km S of Ground (81584-1)(81584-1) | 0 | DECK REPLACEMENT | 0 | 0 | 0
PEACE | TND0025870 | $ | 2026 | 88 | Bear River Bridge on Highway 88, 26 Km SE of Fort Vermilion (78194-1) | 0 | DECK REPLACEMENT
PEACE | TND0025723 | $ | 2026 | 682 | 682:02 Watercourse Culvert on Hwy 682 17 Km W of Fairview (75380-2)(75380-2) | 0 | MISCELLANEOUS CAPITAL BRIDGES | 0 | 0 | 0
PEACE | TND0025052 | $ | 2026 | 692 | 692:02 692:02 km 3.3 Gravina Creek Ditch Erosion (PH092)(692:02 C1 3.299 - 3.300) | 0.001 | SLIDE REPAIR | 0 | 0 | 0
PEACE | TND0025191 | $$ | 2026 | 40 | 40:36 Rock Fall south of McIntyre Mine (GP036)(40:36 C1 12.061 - 12.062) | 0.001 | SLIDE REPAIR | 0 | 0 | 0
PEACE | TND0025216 | $$ | 2026 | 697 | 697:02 18 Km E of Hwy 35 - 39 Km E of Hwy 35(697:02 C1 18.277 - 38.970) | 20.693 | OVERLAY | 42000 | 0 | 0
PEACE | TND0025068 | $ | 2026 | 747 | 747:01 Hwy 665 - Hwy 669(747:01 C1 0.000 - 15.897) | 15.897 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 20000 | 0 | 0
|  |  |  | 665 | 665:02 Hwy 43 - 14 Km E of Hwy 43(665:02 C1 0.000 - 14.450) | 14.45 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 20000 | 0 | 0
SOUTHERN | TND0014195 | $ | 2026 | 2 | 2:15 16 Avenue North Over Deerfoot Trail Interchange, At Calgary (73794-4)(73794-4) | 0 | BRIDGE DECK CONCRETE OVERLAY | 0 | 0 | 0
SOUTHERN | TND0022934 | $ | 2026 | 549 | 549:04 Watercourse Culvert on Provincial Highway 549 near Millarville (78177-1)(78177-1) | 0 | NEW/REPLACE STEEL CULVERT | 0 | 0 | 0
SOUTHERN | TND0024233 | $ | 2026 | 25 | 25:04 Rehabilitate Hwy 25:04 (Hwy. 521 to Hwy. 526) return to gravel state(25:04 C1 0.000 - 19.432) | 19.432 | REHABILITATION | 0 | 39000 | 2000
SOUTHERN | TND0020919 | $$ | 2026 | 547 | 547:04 Hwy 24 - 12 Km S of Hwy 901(547:04 C1 0.000 - 16.700) | 16.7 | OVERLAY | 31000 | 11000 | 26000
SOUTHERN | TND0025671 | $$ | 2026 | 25 | 25:02 1 Km N of Hwy 843 - Hwy 521(25:02 C1 31.350 - 52.724) | 21.374 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 39000 | 2000 | 0
|  |  |  | 519 | 519:06 Hwy 25 - Hwy 845(519:06 C1 0.000 - 12.176) | 12.176 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 14000 | 2000 | 0
|  |  |  | 24 | 24:04 1 km W of Hwy 817 - Hwy 901(24:04 C1 1.100 - 14.500) | 13.4 | THIN OVERLAY (LESS THAN OR EQUAL TO 50MM IN THICKNESS) | 17000 | 1000 | 0
Estimated Tender Construction Value
Symbol | Value At Least | Value Less Than | Meaning
$ | - | $5 Million | Estimated TND Value less than $5 Million
$$ | $5 Million | $10 Million | Estimated TND Value at least $5 Million and less than $10 Million
$$$ | $10 Million | $20 Million | Estimated TND Value at least $10 Million and less than $20 Million
$$$$ | $20 Million | $50 Million | Estimated TND Value at least $20 Million and less than $50 Million
$$$$$ | $50 Million | - | Estimated TND Value $50 Million or greater

## Estimated Value Scale
Estimated Tender Construction Value
Symbol | Value At Least | Value Less Than | Meaning
$ | - | $5 Million | Estimated TND Value less than $5 Million
$$ | $5 Million | $10 Million | Estimated TND Value at least $5 Million and less than $10 Million
$$$ | $10 Million | $20 Million | Estimated TND Value at least $10 Million and less than $20 Million
$$$$ | $20 Million | $50 Million | Estimated TND Value at least $20 Million and less than $50 Million
$$$$$ | $50 Million | - | Estimated TND Value $50 Million or greater